AESOP AI Academy

Kickstarter Campaign Blueprint

PlayAGame.ai™  |  scott@playagame.ai  |  719-244-6690

Confidential Campaign Planning Document — Draft v1.0

AESOP AI Academy is a structured, AI-powered curriculum teaching kids ages 5–18 what artificial intelligence is, how it works, and how to use it responsibly — delivered through the PlayAGame.ai platform with story-based labs, quizzes, and a printable completion certificate.

# 1. Campaign Overview

## Project Title

AESOP AI Academy: AI Literacy for Kids Ages 5–18

## Tagline

"Where every child learns to think with AI — not just use it."

## Category

Education > Games & Learning Technology

## Campaign URL Slug (Suggested)

kickstarter.com/projects/playagame/aesop-ai-academy

## Funding Goal

$12,000 (see Budget Breakdown in Section 7)

## Campaign Duration

30 days (recommended; avoid 60-day campaigns which lose momentum)

## Target Launch Window

Recommended: July 2026, building pre-launch audience through spring/early summer to capitalize on back-to-school awareness and the GenCon 2026 demo (July 30–Aug 2) as a live launch amplifier.

## Short Description (for Kickstarter blurb, 135 chars max)

Teach your child how AI really works. AESOP AI Academy: interactive, story-based AI literacy for ages 5–18.

# 2. The Story: Campaign Page Narrative

## Opening Hook

Your children or students are already using AI every day. Do they know what it is? Do they know what it’s doing to them — and for them? AESOP AI Academy helps them answer that.

## The Problem

AI literacy is the defining skill of the next generation — and most schools aren’t teaching it. Kids are using AI tools without understanding how they work, where their data goes, or how to think critically about AI-generated content. Parents and teachers feel left behind. The tools that exist are either too technical, too dry, or not age-appropriate.

## The Solution

AESOP AI Academy is a structured, browser-based AI literacy program built on the PlayAGame.ai platform. It meets kids where they are — in story, play, and curiosity — and teaches them real AI concepts through age-calibrated lessons, interactive labs, and guided discovery.

Five modules. Six age groups (5–6, 7–8, 9–10, 11–12, 13–15, 16+). 146 total hours of curriculum. No login required for kids. No data collected. COPPA-compliance in progress.

## How It Works

- Choose your child’s age group

- Work through short, story-driven lessons at your own pace

- Complete hands-on labs using PlayAGame.ai’s AESOP Story engine or an LLM

- Pass free lesson quizzes and module tests along the way

- Unlock the paid Curriculum Test to earn a printable certificate

## Why PlayAGame.ai

We built AESOP — a patent-pending AI storytelling and RPG framework — because we believe play is how humans learn best. The AI Academy is the natural extension of that mission: using narrative, creativity, and interactive tools to make hard concepts approachable and memorable.

Our story engine isn’t just a backdrop. It’s the lab. Every lesson has a hands-on activity that students perform directly in AESOP Story or in an AI chat tool, grounding abstract concepts in real experience.

## Who This Is For

- Parents who want to prepare their children for an AI-shaped future

- Homeschool families looking for a structured AI elective

- After-school programs and enrichment instructors

- K-12 educators (especially grades 3–12) seeking supplemental curriculum

- Youth organizations (Scouts, coding clubs, STEM groups)

Closing Hook

- AI isn't coming. It's here — and it's already in your child's hands.

- AESOP AI Academy gives them something no search engine or chatbot ever will: the understanding to use it wisely, question it critically, and shape it confidently.

- Back us on Kickstarter. Help us build the curriculum this generation actually needs.

# 3. Reward Tiers

Kickstarter best practice: 3–5 clean tiers with clear value differentiation. The most popular pledge on Kickstarter is $25 — anchor your core product there. Digital-only rewards fulfill instantly with no shipping complexity.

| Tier | Price | What You Get | Qty / Notes |
| --- | --- | --- | --- |
| Early Explorer (Early Bird) | $10 (limit: 100) |  | EARLY BIRD — first 1000 backers only |
| Young Scholar | $19 | 12-month access to AESOP AI Academy (one age group) + digital welcome kit (PDF poster, certificate frame, AI vocab guide) | Unlimited |
| Family Bundle | $39 | 12-month access to ALL 6 age groups + digital welcome kit + one Curriculum Test unlock (certificate upon pass) | Unlimited — most popular tier |
| Classroom Pack | $79 | Unlimited student access to ALL 6 age groups for 12 months + teacher/facilitator guide PDF + 5 Curriculum Test unlocks + name in credits | Limited: 50 |
| Academy Founding Partner | $199 | Everything in Classroom Pack + permanent "Founding School" credits page listing + direct input session with creator on curriculum roadmap + signed thank-you card | Limited: 20 — highest impact tier |

Note on fulfillment: All rewards are digital or PDF. No physical manufacturing or shipping required. Delivery risk is extremely low. Curriculum Test unlock codes can be issued via email post-campaign.

## Add-Ons (Optional Extras)

- +$5 — Additional Curriculum Test unlock (one extra attempt, any age group)

- +$10 — Printable AESOP AI Academy Wall Certificate Pack (all 6 age groups, blank + fillable PDF)

- +$15 — 30-minute live Q&A session with creator (group session, scheduled monthly during campaign)

# 4. Stretch Goals

Stretch goals keep the campaign alive in the middle weeks and reward the entire backer community. Choose goals that are achievable, visible, and add real value without blowing your delivery timeline.

| Funding Level | Stretch Goal Unlock |
| --- | --- |
| $12,000 (Base Goal) | Fund full production of all 30 lesson units (5 modules × 6 age groups), quizzes, module tests, and Curriculum Test infrastructure. |
| $18,000 | Launch a PARENT + EDUCATOR companion guide: a downloadable PDF with discussion questions, extension activities, and lesson facilitation tips for each module. |
| $25,000 | Unlock AESOP AI Academy ESPANOL: full Spanish-language translation of the curriculum for all 6 age groups. |
| $35,000 | Build the AESOP AI Academy MOBILE APP (iOS + Android) — offline-capable, with progress tracking and push reminders. |
| $50,000 | Commission original illustrated character artwork for the Academy: a cast of 6 age-matched AI Explorer characters, one per group, used throughout the curriculum. |
| $75,000 | Launch the AESOP AI Academy SCHOOL EDITION: an LMS-compatible (Google Classroom, Canvas) version with teacher dashboards, class progress tracking, and roster management. |

# 5. Campaign Video Script (Outline)

## Runtime: ~90 seconds (keep under 2 minutes)

### Opening (0:00–0:10)

Visual: Kids at computers, phones, tablets — everyday AI use. Voice: "Your child is already living in an AI world."

### Problem (0:10–0:25)

Visual: Confused parent, generic AI tool with no explanation. Voice: "But does anyone actually understand what AI is? Most kids — and most adults — don’t. And that’s a problem."

### Solution (0:25–0:50)

Visual: AESOP AI Academy UI — age group selector, lesson view, lab activity in AESOP Story. Voice: "AESOP AI Academy teaches kids ages 5 to 18 what AI really is: how it works, why it matters, and how to use it with confidence and responsibility." Show the curriculum flow: lesson → quiz → lab.

### Differentiator (0:50–1:10)

Voice: "Not another dry textbook. Every lesson has a hands-on lab kids perform right inside AESOP Story — our AI-powered storytelling engine. Learning by doing. Learning through story."

### Call to Action (1:10–1:30)

Visual: Founder on camera. Voice: "I’m Scott, the creator of PlayAGame.ai. I built AESOP because I believe play is how humans learn. This Kickstarter funds the complete AI Academy — all 6 age groups, all 30 lesson units. Back us today and help every child step into the future with confidence."

### Outro (1:30–1:35)

Logo lockup: PlayAGame.ai™ | AESOP AI Academy | playagame.ai

# 6. Pre-Launch Strategy

## 30-Day Pre-Launch Timeline

### Days 1–10: Build the List

- Set up a Kickstarter pre-launch page with a teaser and email capture

- Use a $1 reservation deposit (LaunchBoom-style) instead of just emails — converts 30x higher

- Post teaser content: TikTok + YouTube (you already have a production pipeline)

- Reach out to your verified Colorado Springs school contact list (D11, D49, ASD20, HSD2)

- Post to homeschool Facebook groups, STEM education subreddits, LinkedIn

### Days 11–20: Build Momentum

- Demo at GenCon 2026 (July 30–Aug 2) — hand out QR codes to the Kickstarter pre-launch page

- Send your verified school principal list a teaser PDF with the campaign launch date

- Get 3–5 testimonials from parents/teachers who’ve seen the platform in action

- Record a behind-the-scenes "why I built this" TikTok/YouTube short

### Days 21–30: Final Preparation

- Complete all reward tier descriptions, images, and add-ons in Kickstarter draft

- Prep launch-day email to full list: send night before

- Brief your inner circle (family, PPYMCA connections, improv community) — first pledges matter for social proof

- Test all links, tier images, and reward descriptions on mobile

## Launch Day Protocol

- Launch Tuesday morning 7–10 AM EST

- Send launch email to full list immediately

- Post on all platforms simultaneously

- Ask inner circle to pledge in the first 2 hours

- Go live on TikTok/YouTube that evening to celebrate

# 7. Budget Breakdown

Funding goal: $12,000. All work is solo-developer (Scott), so costs are infrastructure and production support, not salaries.

| Budget Item | Amount | Notes |
| --- | --- | --- |
| Kickstarter + payment processing fees (8%) | $960 | 5% KS + ~3% payment |
| Curriculum content writing & QA (contract assist) | $2,500 | Part-time freelance review |
| UI/UX polish & backend for Curriculum Test tier | $2,000 | Assessment infra (Phase C) |
| Campaign video production | $500 | OBS + Filmora (in-house) + minor editing |
| Marketing & paid ads (pre-launch + active campaign) | $1,500 | Facebook/Instagram targeted |
| Graphic design (reward images, campaign assets) | $500 | Canva + outsourced poster work |
| Domain, hosting, SSL (12 months) | $300 | cPanel / hivetec1 infra |
| Translation tools / Spanish localization start | $500 | Stretch goal seed funding |
| Certificate infrastructure (email + PDF delivery) | $240 | SendGrid + hosting |
| Contingency / unexpected costs (10%) | $1,200 | Buffer |
| TOTAL | $10,200 | ~$1,800 into academy development |

# 8. Risks & Mitigations

## Risk 1: Delivery Delay

Curriculum content takes longer than expected to complete all 30 units.

Mitigation: Deliver core age groups (16–18 and 5–6) first, as those are already planned. Stagger delivery in campaign pledge as two waves. Backers receive access to completed content immediately.

## Risk 2: Low Backer Count

Campaign launches with insufficient pre-launch audience.

Mitigation: Execute 30-day pre-launch strategy with $1 deposit funnel. Leverage GenCon demo (live audience). Use school contact list outreach. Do not launch without 200+ email list.

## Risk 3: Curriculum Test Backend

Phase C (paid Curriculum Test with tracking + certificate) requires backend that doesn’t exist yet.

Mitigation: Reward tiers that include Curriculum Test state this clearly as a Q4 2026 delivery. Lower tiers (access + quizzes) are fully deliverable on launch. No backer is over-promised.

## Risk 4: COPPA Compliance

The platform is applying for COPPA and KidsSAFE seals but does not yet hold them.

Mitigation: Campaign page is transparent about this status. Platform already collects zero personal data from children, making the path to certification straightforward. Seals expected H2 2026.

# 9. Campaign Page Structure

Kickstarter pages are skimmed, not read. Lead with visuals and bold claims. Use short sections with clear headers.

## Recommended Section Order

- HERO: Video + one-line value prop + funding goal progress bar

- THE PROBLEM: 2–3 sentences + striking stat

- THE SOLUTION: What AESOP AI Academy is (screenshot + short description)

- HOW IT WORKS: 3-step visual flow (choose age group → learn → earn certificate)

- THE CURRICULUM: Age group grid, 5 module names, total hours

- WHO IT’S FOR: Badges/icons (Parents / Teachers / Homeschool / Youth Orgs)

- MEET THE CREATOR: Founder photo + 3-sentence bio

- REWARD TIERS: Clean visual tier cards with icons

- STRETCH GOALS: Simple visual with milestone markers

- RISKS & TIMELINE: Production timeline with delivery dates

- FAQ: 5–8 questions, written in advance

## Key Visuals to Produce

- Age group selector screenshot (from AI-Academy.html)

- Lesson view screenshot showing a full module lesson

- Lab activity screenshot (kid doing a story prompt in AESOP Story)

- Certificate mockup (blank + filled example)

- Infographic: 5 modules x 6 age groups grid (30 units visual)

- Founder photo (casual/friendly, not corporate)

## FAQ (Draft)

### Q: Do kids need to log in or create an account?

No. All lesson content and free quizzes are fully accessible without login. The paid Curriculum Test (for the printable certificate) requires a parent/adult account only.

### Q: What devices does it work on?

AESOP AI Academy is browser-based and works on desktop, tablet, and mobile. An offline mobile app is a stretch goal at $35,000.

### Q: Is this aligned with school standards?

The curriculum was built with AI literacy frameworks in mind, including ISTE and CSTA guidelines. A formal school-edition LMS integration is a stretch goal at $75,000.

### Q: When will I get access?

Digital access rewards are delivered within 30 days of campaign close. The Curriculum Test tier (paid certificate) is targeted for Q4 2026 and backers will receive advance access codes.

### Q: What if the campaign doesn’t hit its goal?

Kickstarter is all-or-nothing. If we don’t reach $12,000, no one is charged and the campaign does not fund. We are fully committed to the goal and to our pre-launch audience strategy.

# 10. Key Metrics to Track

- Email/reservation list size before launch (target: 500+)

- Day 1 funding percentage (target: 30%+ funded in first 48 hours)

- Most-selected reward tier (expected: Family Bundle at $39)

- Backer comment and share rate

- Traffic source breakdown (email vs. social vs. Kickstarter discovery)

- Daily pledge velocity (identify mid-campaign slump for flash reward activation)

Mid-campaign slump strategy: Prepare a "Flash Reward" in advance — a 48-hour tier offering a bonus add-on (e.g., free Certificate Pack) for any pledge made during the window. Announce on Day 15 to reignite momentum.

PlayAGame.ai™ | AESOP AI Academy Kickstarter Blueprint | Confidential | v1.0