AESOP AI ACADEMY FOR YOUTH

MULTILINGUAL DELIVERY PLAN

🇺🇸 English ¦ 🇫🇷 French ¦ 🇩🇪 German ¦ 🇪🇸 Spanish ¦ 🇨🇳 Chinese ¦ 🇰🇷 Korean

This document defines the architecture, phasing, technical requirements, translation approach, and cultural localization guidelines for delivering the AESOP AI Academy for Youth curriculum in six languages. English is the master/source language. All other languages are derived from the English master content set following the same master-first, subset-by-age architecture.

This document is a planning supplement to: AI-Academy-Curriculum-Plan.docx, AI-Academy-Time-Structure.docx, AI-Academy-Assessment-Architecture.docx, and AI-Academy-Curriculum-Outline.docx.

# Scale of Work

Delivering the full AI Academy curriculum in 6 languages represents a significant content and engineering effort. The table below summarizes the total scope:

| Metric | Count | Notes |
| --- | --- | --- |
| Languages | 6 | English (master) + French, German, Spanish, Chinese, Korean |
| Age groups | 6 | Ages 5-6, 7-8, 9-10, 11-12, 13-15, 16-18 |
| Modules | 5 | What AI Is, Safety & Ethics, Responsible Use, Storytelling, Careers |
| Teaching units (EN) | 30 | 6 age groups x 5 modules |
| Total language versions | 180 | 30 units x 6 languages |
| Avg lessons per unit | 4 | Ranges from 3 (ages 5-6) to 5 (ages 16-18) |
| Total lesson content pieces | ~720 | All languages combined |
| Total labs (all languages) | ~720 | One lab per lesson across all languages |
| Total quiz plans (all languages) | 180 | One per teaching unit per language |
| Total module tests (all languages) | 180 | One per teaching unit per language |
| Curriculum test versions | 36 | 6 age groups x 6 languages (shared structure, translated content) |
| Certificate variants | 36 | 6 age groups x 6 languages |

Note: These numbers assume all English content is final before translation begins. Translating content that is still changing wastes translation effort. English master must be locked before Phase 1 translation starts.

# Languages — Summary and Priority

French, German, and Spanish use Latin scripts and are technically simpler to implement. Chinese and Korean require additional font loading and have distinct cultural localization needs. All six are in scope; a two-phase rollout is recommended.

| Language | Code | Script/Font Notes | Register Considerations | Priority |
| --- | --- | --- | --- | --- |
| 🇺🇸 English | EN | Latin; Arial/system font | Informal for 5-12; progressively more formal for 13-18 | Source |
| 🇫🇷 French | FR | Latin + accents (e, a, u, etc.); UTF-8 required; Arial handles correctly | Use "tu" for all ages in lessons; "vous" optional for 16-18 formal writing tasks only | Phase 1 |
| 🇩🇪 German | DE | Latin + umlauts (a, o, u) + eszett; UTF-8; Arial handles correctly | Du-form throughout; Sie-form only in example professional correspondence for 16-18 | Phase 1 |
| 🇪🇸 Spanish | ES | Latin + accents + enye; UTF-8; Arial handles correctly | Tuteo (tu) throughout; voseo awareness note for LatAm users where relevant | Phase 1 |
| 🇨🇳 Chinese | ZH | CJK Unified Ideographs; requires CJK web font (Noto Sans SC or similar); font stack must include fallback | Simplified characters; age-appropriate vocabulary tiers; pinyin may help 5-8 age group | Phase 2 |
| 🇰🇷 Korean | KO | Hangul syllables; requires Hangul web font (Noto Sans KR or similar); font stack must include fallback | Haeyoche (해요체) for all ages; jeondaemal (formal speech) introduced in 16-18 professional contexts | Phase 2 |

# Translation Approach by Content Type

Not all content requires the same translation rigor. The approach scales with stakes: youngest age content and credentialing content require the highest review level; structural UI text requires the least.

| Content Type | Translation Approach | Review Required | Localization Notes |
| --- | --- | --- | --- |
| Lesson narrative text | AI-assisted translation (Claude) + human review for 11-18 age groups; AI + parent/teacher review for 5-10 | Human native speaker review required for all published text | Cultural references (e.g., Pixar examples) must be localized to culturally familiar equivalents per language |
| Quiz questions and answers | AI translation + logic check — answer choices must still be clearly distinct and unambiguous after translation | Logic review for every quiz answer set; wrong answer explanations especially critical | Avoid idiomatic English that translates to identical meaning options |
| Lab instructions | AI translation + practical review — steps must be actionable in the target language context | Verify tool names (AESOP, Claude, ChatGPT) appear correctly; some tools may have local equivalents | For Chinese and Korean: verify that referenced platforms (Google, YouTube) are available or provide alternatives |
| Age 5-6 and 7-8 content | AI translation + mandatory native speaker parent/teacher review; read-aloud testing recommended | Highest review priority — errors in youngest age content are most harmful | Vocabulary must be validated by a native-speaking educator; not just a translator |
| Professional/technical content (16-18) | AI translation with domain expert review for technical accuracy | Technical terminology (backpropagation, RLHF, EU AI Act) must use accepted terminology in each language | German and Chinese have established technical AI vocabulary; Korean is still evolving — note where English terms are standard |
| Certificate text | Professional human translation only — this is a legal/credential document | Native speaker legal/formal review required; tone must be appropriately formal | Certificate must use full formal register in all languages; date formats must follow local convention |
| UI navigation and labels | AI translation + UX review for button text length — Chinese/Korean are more compact; German can be long | Check text does not overflow buttons or truncate critically | German compound words can cause significant UI overflow; design buttons to accommodate 40% longer text |
| Printable assessment questions (curriculum test) | Professional human translation; retranslation into English for back-check | Back-translation quality check required for all curriculum test content | Ambiguity in any answer choice must be resolved before publishing |

General principle: AI-assisted translation (Claude) is appropriate for a first draft of all content. Human native-speaker review is required before any content is published. The younger the age group, the more critical the human review.

# Technical Implementation Requirements

The AI-Academy.html file requires these technical changes to support all 6 languages:

| Requirement | EN/FR/DE/ES | ZH (Chinese) | KO (Korean) |
| --- | --- | --- | --- |
| Web font | Arial / system-ui (already supported) | Add Noto Sans SC or Source Han Sans (Google Fonts); fallback: system CJK font | Add Noto Sans KR or Nanum Gothic (Google Fonts); fallback: system Hangul font |
| Character encoding | UTF-8 (already set) | UTF-8 required; confirm all HTML files declare charset correctly | UTF-8 required; confirm charset meta tag present |
| HTML lang attribute | lang="en" | lang="zh-Hans" for Simplified; lang="zh-Hant" for Traditional | lang="ko" |
| Text direction | LTR (default) | LTR (Simplified Chinese reads LTR) | LTR (Korean reads LTR; vertical text is optional/decorative only) |
| Button/UI text length | Baseline | Chinese is typically 40-60% shorter than English — buttons may look too empty; adjust padding | Korean is similar length to English — minimal adjustment needed |
| Input fields (labs) | Standard Latin keyboard | May need IME (Input Method Editor) support note for users; no code change needed — browser handles | Requires IME support note; browser-native IME handles input |
| Quiz answer rendering | Standard | Ensure CJK font renders at correct size in quiz option buttons; test at 16px minimum | Ensure Hangul renders correctly in quiz buttons; test at 16px minimum |
| Number/date formats | MM/DD/YYYY (US) | YYYY/MM/DD for China; YYYY년 MM월 DD일 for Korea on certificates | YYYY년 MM월 DD일 on certificates |
| File naming convention | AI-Academy-en.html | AI-Academy-zh.html | AI-Academy-ko.html |

## Language Selector Implementation

The language selector must be added to the UI before any translation work is done. Two options:

- Option A — Single file per language: AI-Academy-en.html, AI-Academy-fr.html, AI-Academy-de.html, etc. Simpler to build and maintain. URL-based language switching. Recommended.

- Option B — Single file with language switching: All languages in one file, JS switches content on selection. More complex; significantly larger file size; not recommended for CJK content.

Recommendation: Option A (separate files per language). Simpler architecture, easier to maintain, better performance for CJK fonts.

## Font Stack Recommendation

Add to CSS for Chinese: font-family: "Noto Sans SC", "Source Han Sans CN", "Microsoft YaHei", sans-serif

Add to CSS for Korean: font-family: "Noto Sans KR", "Nanum Gothic", "Malgun Gothic", sans-serif

Both Noto Sans SC and Noto Sans KR are available via Google Fonts at no cost and include full character coverage.

# Delivery Phase Plan

Recommended sequencing to manage risk and get value early. Phase 0 (English completion) is the hard prerequisite for everything else.

| Phase | Scope | Languages | Deliverables | Prerequisite |
| --- | --- | --- | --- | --- |
| Phase 0 | English master content complete + tested | English only | All 30 teaching units built and reviewed in English; labs tested; quizzes verified | None — must complete before any translation begins |
| Phase 1a | Infrastructure + language selector | All 6 | Language selector UI added to AI-Academy.html; HTML lang/font support for all 6 languages; file naming convention established | Phase 0 complete |
| Phase 1b | Module 1 pilot translation (What AI Is) | FR, DE, ES | All 6 age groups of Module 1 translated to French, German, Spanish; reviewed; tested in browser | Phase 1a complete; native reviewers engaged |
| Phase 1c | Module 1 pilot translation | ZH, KO | All 6 age groups of Module 1 translated to Chinese and Korean; CJK fonts tested; reviewed | Phase 1b complete; CJK fonts integrated |
| Phase 2 | Modules 2-5 translation (FR, DE, ES) | FR, DE, ES | All remaining 4 modules translated for Latin-script languages; reviewed; curriculum test translated | Phase 1 complete for FR/DE/ES |
| Phase 3 | Modules 2-5 translation (ZH, KO) | ZH, KO | All remaining 4 modules in Chinese and Korean; full review cycle; curriculum test translated | Phase 1 complete for ZH/KO |
| Phase 4 | Certificate localization | All 6 | 36 certificate variants (6 languages x 6 age groups); formal register; date/name format per locale | Phases 2 and 3 complete |
| Phase 5 | QA and launch | All 6 | Full browser testing across languages; age group content spot-check; native speaker final sign-off | Phase 4 complete |

Critical path note: Do not begin translation of any module until the English version of that module has been reviewed and approved. Translating draft content that later changes is waste.

# Cultural Localization Requirements

Translation alone is insufficient. Each language version requires cultural adaptation of examples, references, platforms, and social context. The table below captures the most critical localization decisions per language:

| Issue | FR | DE | ES | ZH | KO |
| --- | --- | --- | --- | --- | --- |
| AI governance reference (EU AI Act) | Directly relevant — France is EU | Directly relevant — Germany is EU | Spain is EU; LatAm contexts differ — add note | Replace with China AI regulations | Replace with Korean AI laws (AI Framework Act 2024) |
| Cultural career examples | Localize company examples to include French AI firms (Mistral) | Include German AI ecosystem (SAP, Aleph Alpha) | Include Spanish/LatAm examples | Chinese AI ecosystem (Baidu, Alibaba DAMO, Tencent) | Korean AI ecosystem (Naver, Kakao, Samsung AI) |
| Story and activity examples | French cultural context for younger ages; characters with French names | German cultural context; familiar settings | Neutral/LatAm-friendly; diverse name representation | Chinese cultural context; familiar settings for Chinese learners | Korean cultural context; school/family settings common |
| Platform availability (labs) | All referenced platforms available | All referenced platforms available | All referenced platforms available | Google/YouTube blocked in mainland China — provide Baidu/Bilibili alternatives or note | All referenced platforms available in Korea |
| School structure references | Adapt grade level references to French system (CE1, CM2, etc.) | Adapt to German Gymnasium/Grundschule system | Adapt to regional systems; avoid US-specific references | Adapt to Chinese school system (xiao xue, chu zhong) | Adapt to Korean school system (초등학교, 중학교) |
| Honorifics / politeness | Tu throughout for learners; note formal register for 16-18 | Du throughout; Sie only in explicit professional examples | Tuteo throughout; voseo note where relevant | Age-appropriate vocabulary tiers; no direct honorific challenge | Critical: haeyoche throughout; jeondaemal in 16-18 professional content; speech levels affect all content |

## Special Case: Chinese Platform Availability

Several lab activities reference platforms that are blocked or restricted in mainland China: Google Search, YouTube, and some LLM tools. The Chinese version of each affected lab must:

- Identify which tools are blocked (currently: Google, YouTube, some Claude API access)

- Provide mainland China-appropriate alternatives (Baidu, Bilibili, Kimi/Moonshot, Qwen/Tongyi)

- Add a note for users outside mainland China (Taiwan, HK, Singapore, overseas Chinese learners) who can use the original tools

- Flag this as a required review step for every lab in the Chinese version

## Special Case: Korean Speech Levels

Korean has a grammatically distinct honorific system that fundamentally affects sentence construction. The AI Academy Korean content must use haeyoche (polite informal, -아/어요 endings) throughout all age groups. Age 16-18 professional content should introduce jeondaemal where examples involve workplace or formal academic writing, but all instructional text remains in haeyoche. This is a review requirement, not just a stylistic note — incorrect speech levels in Korean content for children will be noticed immediately by native speakers and undermine credibility.

# Quality Assurance Requirements

## Minimum Review Standards

- Every published lesson: reviewed by one native speaker of that language who is also familiar with children or adolescent education

- Age 5-8 content: additionally reviewed by a native-speaking parent or primary school teacher

- Age 16-18 technical content: additionally reviewed by a native speaker with AI/tech domain knowledge

- Curriculum test questions: back-translated to English by a second translator and compared against original for meaning drift

- Certificate text: reviewed by a native speaker with formal/legal register experience

- Lab instructions: tested by a native speaker actually completing the lab to verify instructions are clear and actionable

## Consistency Requirements

- Maintain a translation glossary per language for AI terminology: the same English term must always translate to the same target-language term

- Key terms to standardize per language: Artificial Intelligence, machine learning, neural network, large language model, training data, prompt, context window, alignment, bias, deepfake

- AESOP, PlayAGame.ai, and AI Academy remain as proper nouns in all languages — do not translate

- Lab location references (PlayAGame.ai, Claude, ChatGPT) remain in English as proper names

# Ongoing Maintenance

When English master content is updated (new lessons, revised quizzes, updated labs), the following maintenance process applies:

- Flag the changed English content in a change log

- Determine scope: is this a minor wording update (re-translate that section only) or a structural change (re-review the full unit)

- Apply the change to all 5 non-English versions

- Re-review changed sections per the QA standards above

- Update version numbers on all affected language files

Recommendation: Maintain a centralized change log (spreadsheet or document) tracking every change to English master content with: date, module, age group, change type, and status of translation update per language.

Next Step: Confirm language list and priority order. Then build language selector UI before any translation work begins.

Multilingual Delivery Plan v1.0  |  PlayAGame.ai  |  AESOP AI Academy for Youth